## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-SWEN-261-03-6
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page. |  | 3/8 OV Passed |  | Passed
| Given that I am not on the Products page when I choose the Products page then I am taken to the Products page. |  | 3/20 OV Passed |  | Passed
| Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available. |  | 3/20 JS Passed |  | Passed
| Given that I am on the products page when there are products in the inventory then I see each product and short description. |  | 3/20 JS Passed |  | Passed
| Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart. |  | 3/23 JS Passed |  | Passed
As an Owner I want to login to the site so that the inventory management system can be locked behind my account and only authorize changes from me. | Given I am the owner when I login with my owner username then should be directed to the owner page. |  | 3/22 KW Passed |  | Passed
| Given I am the customer when I login with my customer username then I shouldn't be directed to the owner page. |  | 3/22 KW Passed |  | Passed
As a Buyer I want to search products by name so that they are easier to find. | Given I search a product object when product with the given name exists then the system should return the product object and a status code of 200 (OK). |  | 3/20 KF Passed |  | Passed
| Given I search a product object when no product with the given name exists then the system should return a status code of 404 (NOT FOUND). |  | 3/20 KF Passed |  | Passed
As a Buyer I want to see a list of products so that I can choose what to purchase. | Given I submit a request for the inventory when products exist in the inventory then the system should return a list of products and a status code of 200 (OK). |  | 3/20 OV Passed |  | Passed
| Given I submit a request for the inventory when no products exist in the inventory then the system should return an empty list of products and a status code of 200 (OK). |  | 3/20 OV Passed |  | Passed
As a Buyer I want to add and remove products from a virtual shopping cart so that I can prepare a list of them for checkout. | Given I add a product to cart when products exist in the inventory then the system should return the product added to cart and a status code of 200 (OK). |  | 3/23 JS Passed |  | Passed
| Given I remove a product from cart when the product does not exist in the cart then the system should return a status code of 404 (NOT FOUND). |  | 3/23 OV Passed |  | Passed
As a Buyer I want to check out my products so that I can buy and receive them. | Given I checkout the current cart when products exist in the cart then the system should return the products purchased and a status code of 200 (OK). |  | 3/23 OV Passed |  | Passed
| Given I checkout the current cart when no products exist in the cart then the system should return a status code of 404 (NOT FOUND). |  | X |  | 4/4 KF Passed - if there are no items in your cart, you can't checkout, if the items in your cart are unavailable, you will receive the message and can't checkout
As an Owner I want to remove products from the inventory so that I can remove any products that should no longer be available for purchase. | Given I want to delete a product from inventory when the product exists in the inventory then I can delete the specific product from inventory using a button on the front-end. |  | 3/20 JS Passed |  | Passed
As an Owner I want to edit a product in the inventory so that I can modify any currently available products if changes are needed. | Given I go to view the entire inventory on the front-end when products exist in the inventory then the application should display a list of products and the system should return a status code of 200 (OK). |  | 3/20 KW Passed |  | Passed
| Given I go to view the entire inventory when no products exist in the inventory then the system should display no products and the system should return a status code of 200 (OK). |  | 3/20 KW Passed |  | Passed
As an Owner I want to add a product to the inventory so that I can show a new product that is available for purchase. | Given I create a new product when I click to add the product then the product should be added to the inventory for users to see. |  | 3/22 KF Passed |  | Passed
As an Owner I want to save my inventory so that Buyers can see an updated inventory when they login. | Given I am the owner when exit the site then the products I edited or added should stay in the inventory for users to see. |  | 3/22 KF Passed |  | Passed
As an Owner or Buyer I want to create a custom product so that I create a design that appeals specifically to me. | Given I am making a custom flag when I choose a flag color and text then the custom flag should change to my picked color and text. |  | X |  | X
As an Owner or Buyer I want to save a custom product so that I can come back to it later and buy it. | Given a custom product when a user presses save then I expect the custom product will be saved to the user inventory. |  | X |  | X
As a Buyer I want to purchase my custom products so that I can own it and display it in real life. | Given a set of options when I select a customization option then I expect that option to affect the picture of the product. |  | X |  | X
| Given a customizable product when I select add to cart I expect the customized item to be added to cart. |  | X |  | X
As an Owner, I want to give my products categories so that my Buyers can see details about the products. | Given a product when I select tags for that product I expect that product to retain the tags. |  | X |  | X
| Given a product when I select no tags, I expect that the product will have no tags. |  | X |  | X
As a Buyer, I want to use the filter option so that I can see a list of products that fit in the category I chose. | Given that all products meet a condition, when I select that condition to filter items, I expect to see a list of all items. |  | X |  | X
| Given a list of filters, when I select no filter, I expect no filter to be applied. |  | X |  | X
| Given that no item matches a certain filter when I select that filter I expect to see a "no results" message. |  | X |  | X